## Sheet1
Meeting Date | Meeting Time | Meeting Place (online/in-person) | Discussions | Outcomes | Meeting Duration | Type | Attendees
2023-10-04 | 16:00 | Online | * Discussed Assignment instructions. * Decided tentative dates for each sub-deliverable and next meeting times internally. * Went through rubric. | * Got understanding of the assignment requirements. | 20 min | Internal | 2 - Aditya Purohit, Aditya Pattani
2023-10-11 | 17:00 | Online | * Discussed Background research done by individual. | * Prepared a merged version of background research. | 40 min | Internal | 2 - Aditya Purohit, Aditya Pattani
2023-10-12 | 18:45 | Online | The team shared the background research performed and collated by both the members. The team shared their understanding of the hotel details captured and what entities they included Team to begin working on the conceptual model, so that they can finalize on the relationships and fix design issues Team to write assumptions in the report regarding how they're approaching the problem The summary section of the report will contain how the team approached the problem at hand and their learnings for the same | The team is to create a Chen model for the report highlighting all the entities and fixing design issues as and when encountered | 15 min | TA | 3 - TA Arpitkumar, Aditya Purohit, Aditya Pattani
2023-10-22 | 18:45 | Online | Showed the Conceptual Phase completion with an ER Diagram(Chen Model) Showed the Entity & Reasoning related table, which was added in report, as per previous meeting feedback. Finding Design Issues & fixing them is in progress. Logical Phase to be started soon after design issues are fixed. | - | 15 min | TA | 3 - TA Arpitkumar, Aditya Purohit, Aditya Pattani
2023-10-27 | 19:00 | Online | * Discussed th progress this DB conceptual model | - | 10 min | Professor | 3 - Professor Saurabh Dey, Aditya Purohit, Aditya Pattani
2023-10-31 | 20:00 | Online | * Went through the progress made by each team member * Discussed existence of fan traps, chasm traps, historical data and began discussion on normalization of our entities | * Identified a fan trap and noted a requirement for a historical table in our ER diagram | 1 hour 30 mins | Intenal | 2 - Aditya Purohit, Aditya Pattani